## Read me
NESR SCMS configuration register
Team 3. Satellite communication and observation along the sea route in all weather conditions with monitoring of ice conditions.
Repository: https://github.com/VladZg/NESR
Configuration manager
Jash Joshi (proposed). Backup for model and requirements files: Vladislav Zagorodnyuk.
Sheets
CI register: every configuration item (CI): owner, version, status, PDR deliverable, path in the repository.
PDR checklist: the 9 PDR deliverables of the course, their primary CI and progress of all CIs that belong to each.
By member: CIs per team member and their status.
Folders: repository folders and number of CIs in each.
Baselines: planned baselines and git tags.
Change log: one row per new version of a CI.
Rules (full text in CONTRIBUTING.md)
1. File name: T3_<CAT>-<NNN>_<Short-Title>.<ext>. No version, date or status in the name; git keeps the history.
2. Version vMAJOR.MINOR lives here and in the document header: v0.x drafts (+0.1 per merged pull request), v1.0 at the PDR baseline, v1.x after an approved change request.
3. Every pull request that adds or changes a CI updates its row here (Version, Status, Last update) and adds a Change log row.
4. Baselines are git tags plus GitHub Releases: srr-baseline, pdr-v1.0.
Yellow cells are edited by CI owners and the configuration manager; grey cells are formulas.

## CI register
CI ID | Title | Category | Owner | Formats | Version | Status | PDR item | Path in repository | In repo | Last update | Notes
MGT-001 | Configuration register | MGT | Jash Joshi | xlsx | v0.2 | Draft | 8 | 08_Configuration_Data_Management/T3_MGT-001_Configuration-Register.xlsx | Yes | 2026-10-29 | Single source of truth for all CIs
MGT-002 | Product card (repository README.md) | MGT | Jash Joshi | md | v0.1 | Draft |  | README.md | Yes | 2026-10-29 | Stored as README.md
MGT-003 | Project management plan | MGT | Jash Joshi | md | v0.1 | Draft | 4 | 04_Project_Management/T3_MGT-003_Project-Management-Plan.md | Yes | 2026-10-29 | Starter text, to complete
MGT-004 | Team roles and responsibilities | MGT | Jash Joshi | md | v0.1 | Draft | 4 | 04_Project_Management/T3_MGT-004_Team-Roles.md | Yes | 2026-10-29 | Inside the project management plan
MGT-005 | Schedule and milestones | MGT | Jash Joshi | md | - | Planned | 4 | 04_Project_Management/T3_MGT-005_Schedule-and-Milestones.md | No |  | Dates of SRR and PDR to add
MGT-006 | Work breakdown structure | MGT | Jash Joshi | csv | v0.1 | Draft | 4 | 04_Project_Management/T3_MGT-006_WBS.csv | Yes | 2026-10-29
MGT-007 | Configuration and data management baseline plan | MGT | Jash Joshi | md | v0.1 | Draft | 8 | 08_Configuration_Data_Management/T3_MGT-007_CM-DM-Baseline-Plan.md | Yes | 2026-10-29
MGT-008 | Naming, versioning and review rules (CONTRIBUTING.md) | MGT | Jash Joshi | md | v0.1 | Draft | 8 | CONTRIBUTING.md | Yes | 2026-10-29 | Stored as CONTRIBUTING.md
REQ-001 | Mission statement, needs, goals, objectives and MOEs | REQ | Jash Joshi | md | v0.1 | Draft | 2 | 03_Requirements/T3_REQ-001_Mission-Statement-and-NGO.md | Yes | 2026-10-29
REQ-002 | Stakeholder register | REQ | Jash Joshi | md | v0.1 | Draft | 1 | 03_Requirements/T3_REQ-002_Stakeholder-Register.md | Yes | 2026-10-29 | Also a sheet in REQ-003
REQ-003 | System (SR) and technical (TR) requirements with traceability | REQ | Vladislav Zagorodnyuk | xlsx, md | v0.3 | Draft | 3 | 03_Requirements/T3_REQ-003_System-and-Technical-Requirements.xlsx 03_Requirements/T3_REQ-003_System-and-Technical-Requirements.md | Yes | 2026-10-29 | 11 SR, 32 TR
REQ-004 | Similar missions review and RADARSAT requirements analysis | REQ | Vladislav Zagorodnyuk | md | - | Planned |  | references/T3_REQ-004_Reference-Missions-Review.md | No
REQ-005 | Compliance check with maritime regulations | REQ | Mikhail Timofeenko | csv | v0.1 | Draft | 9 | 09_Maritime_Compliance/T3_REQ-005_Maritime-Compliance-Matrix.csv | Yes | 2026-10-29 | Starter matrix, statuses to confirm
CON-001 | Concept of operations | CON | Jash Joshi | md | v0.1 | Draft | 2 | 02_ConOps/T3_CON-001_ConOps.md | Yes | 2026-10-29 | Starter text with scenarios S1 to S6
CON-002 | Scenario map: functional chains S1 to S6 | CON | Vladislav Zagorodnyuk | svg, png | v0.1 | Draft | 2 | 02_ConOps/T3_CON-002_Scenario-Map.svg 02_ConOps/T3_CON-002_Scenario-Map.png | Yes | 2026-10-26
ARC-001 | IDEF0 A-0 context diagram | ARC | Victoria Kulikova | svg, png | v0.1 | Draft | 1 | 01_MBSE_Model/functional_analysis/T3_ARC-001_IDEF0-A-0-Context.svg 01_MBSE_Model/functional_analysis/T3_ARC-001_IDEF0-A-0-Context.png | Yes | 2026-10-27
ARC-002 | IDEF0 A0 decomposition | ARC | Victoria Kulikova | svg, png | v0.1 | Draft | 1 | 01_MBSE_Model/functional_analysis/T3_ARC-002_IDEF0-A0-Decomposition.svg 01_MBSE_Model/functional_analysis/T3_ARC-002_IDEF0-A0-Decomposition.png | Yes | 2026-10-22
ARC-003 | IDEF0 A4 Deliver commands to ships | ARC | Vladislav Zagorodnyuk | svg, png | v0.1 | Draft | 1 | 01_MBSE_Model/functional_analysis/T3_ARC-003_IDEF0-A4-Deliver-Commands.svg 01_MBSE_Model/functional_analysis/T3_ARC-003_IDEF0-A4-Deliver-Commands.png | Yes | 2026-10-26
ARC-005 | N2 diagram of system interfaces | ARC | Victoria Kulikova | png | - | Planned | 7 | 07_Interface_Management/T3_ARC-005_N2-Diagram.png | No
ARC-006 | Interface control documents ICD-01 to ICD-06 | ARC | Victoria Kulikova | md | - | Planned | 7 | 07_Interface_Management/T3_ARC-006_ICD-List.md | No |  | Listed in ARC-009
ARC-009 | Interface management plan | ARC | Victoria Kulikova | md | v0.1 | Draft | 7 | 07_Interface_Management/T3_ARC-009_Interface-Management-Plan.md | Yes | 2026-10-29 | Starter text with interface list
MOD-001 | Capella project NESR SCMS (.capella, .aird) as zip | MOD | Vladislav Zagorodnyuk | zip | v0.1 | Draft | 1 | 01_MBSE_Model/capella/T3_MOD-001_Capella-Model.zip | No |  | To upload; fix typo 'montoring' in model name
MOD-002 | OAB Operational Architecture Blank | MOD | Vladislav Zagorodnyuk | png | v0.1 | Draft | 1 | 01_MBSE_Model/diagrams/1_Operational_Analysis/T3_MOD-002_OAB-Operational-Architecture.png | Yes | 2026-10-19
MOD-003 | OEBD Operational Entity Breakdown | MOD | Vladislav Zagorodnyuk | png | v0.1 | Draft | 1 | 01_MBSE_Model/diagrams/1_Operational_Analysis/T3_MOD-003_OEBD-Operational-Entities.png | Yes | 2026-10-19 | GLONASS is MEO, not GSO: fix label
MOD-004 | OCB Operational Capabilities Blank | MOD | Vladislav Zagorodnyuk | png | v0.1 | Draft | 1 | 01_MBSE_Model/diagrams/1_Operational_Analysis/T3_MOD-004_OCB-Operational-Capabilities.png | Yes | 2026-10-19
MOD-005 | CSA Contextual System Actors | MOD | Vladislav Zagorodnyuk | png | v0.1 | Draft | 1 | 01_MBSE_Model/diagrams/2_System_Analysis/T3_MOD-005_CSA-Contextual-System-Actors.png | Yes | 2026-10-27
MOD-006 | SDFB with functional chains S1, S3a, S3b, S6 | MOD | Vladislav Zagorodnyuk | svg | v0.1 | Draft | 1 | 01_MBSE_Model/diagrams/2_System_Analysis/T3_MOD-006_SDFB-Root-System-Function.svg | Yes | 2026-10-27
MOD-007 | SAB System Architecture Blank | MOD | Vladislav Zagorodnyuk | png | v0.1 | Draft | 1 | 01_MBSE_Model/diagrams/2_System_Analysis/T3_MOD-007_SAB-System-Architecture.png | Yes | 2026-10-27
MOD-008 | System Analysis diagrams package (CSA, SDFB, SAB) | MOD | Vladislav Zagorodnyuk | pdf | v0.1 | Draft | 1 | 01_MBSE_Model/diagrams/2_System_Analysis/T3_MOD-008_System-Analysis-Diagrams.pdf | Yes | 2026-10-27 | Submitted for problem set 2
MOD-009 | Exchange scenarios (ES) for S2 and S6 | MOD | Vladislav Zagorodnyuk | png | - | Planned | 1 | 01_MBSE_Model/diagrams/2_System_Analysis/T3_MOD-009_ES-Exchange-Scenarios.png | No
MOD-010 | Logical architecture (LAB, LFBD) in Capella | MOD | Victoria Kulikova | png | - | Planned | 1 | 01_MBSE_Model/diagrams/3_Logical_Architecture/T3_MOD-010_LAB-Logical-Architecture.png | No |  | Required by PDR item 1
SIM-001 | Kondor-FKA coverage and revisit over the NSR | SIM | Vladislav Zagorodnyuk | py | - | Planned | 3 | analysis/T3_SIM-001_SAR-Coverage-and-Revisit.py | No |  | Confirms TR-13 (24 h TBR)
SIM-002 | Communication coverage and availability, 66 to 82 deg N | SIM | Vladislav Zagorodnyuk | py | - | Planned | 3 | analysis/T3_SIM-002_Comms-Availability.py | No |  | Verifies TR-09
SIM-003 | End-to-end latency budget | SIM | Vladislav Zagorodnyuk | xlsx | - | Planned | 3 | analysis/T3_SIM-003_Latency-Budget.xlsx | No |  | Verifies TR-10, TR-11, TR-14
SIM-004 | Trade study: LEO vs HEO communication architecture | SIM | Vladislav Zagorodnyuk | xlsx | - | Planned |  | analysis/T3_SIM-004_Trade-Study-LEO-vs-HEO.xlsx | No
SAF-001 | Risk register (5x5) | SAF | Mikhail Timofeenko | csv | v0.1 | Draft | 5 | 05_Risk_Analysis/T3_SAF-001_Risk-Register.csv | Yes | 2026-10-29 | Seeded with 7 risks
SAF-002 | FMEA: on-board terminal and ground platform | SAF | Mikhail Timofeenko | xlsx | - | Planned | 5 | 05_Risk_Analysis/T3_SAF-002_FMEA.xlsx | No
SAF-003 | Reliability and availability analysis | SAF | Mikhail Timofeenko | xlsx | - | Planned | 5 | 05_Risk_Analysis/T3_SAF-003_Reliability-and-Availability.xlsx | No |  | Verifies TR-23, TR-24
VV-001 | Verification cross-reference matrix | VV | Mikhail Timofeenko | csv | v0.1 | Draft | 6 | 06_Verification_Validation/T3_VV-001_VCRM.csv | Yes | 2026-10-29 | Generated from REQ-003
VV-002 | System verification and validation plan | VV | Mikhail Timofeenko | md | v0.1 | Draft | 6 | 06_Verification_Validation/T3_VV-002_VV-Plan.md | Yes | 2026-10-29 | Starter text
PS-002 | Problem set 2: System Analysis (CSA, SDFB, SAB, ES) | PS | Vladislav Zagorodnyuk | md | v0.1 | Draft |  | problem-sets/PS02_System_Analysis/README.md | Yes | 2026-10-27 | Files in 01_MBSE_Model
REV-001 | PDR presentation | REV | All (CM assembles) | pptx | - | Planned |  | reviews/T3_REV-001_PDR-Presentation.pptx | No
REF-001 | References: NASA SE Handbook, reference missions, standards | REF | Jash Joshi | md | v0.1 | Draft |  | references/T3_REF-001_References.md | Yes | 2026-10-29

## PDR checklist
# | PDR deliverable | Folder | Owner | Primary CI | Primary CI status | CIs | Planned | Draft or in review | Baselined | Progress
1 | MBSE model in Arcadia-Capella: stakeholders, operational analysis, system analysis, logical architecture | 01_MBSE_Model | Vladislav Zagorodnyuk | MOD-001 | Draft | 14 | 2 | 12 | 0 | 42.86%
2 | ConOps of the proposed system | 02_ConOps | Jash Joshi | CON-001 | Draft | 3 | 0 | 3 | 0 | 50%
3 | Clear set of technical requirements | 03_Requirements | Vladislav Zagorodnyuk | REQ-003 | Draft | 4 | 3 | 1 | 0 | 12.5%
4 | Project management plan including WBS | 04_Project_Management | Jash Joshi | MGT-003 | Draft | 4 | 1 | 3 | 0 | 37.5%
5 | Risk analysis | 05_Risk_Analysis | Mikhail Timofeenko | SAF-001 | Draft | 3 | 2 | 1 | 0 | 16.67%
6 | System verification and validation plans | 06_Verification_Validation | Mikhail Timofeenko | VV-002 | Draft | 2 | 0 | 2 | 0 | 50%
7 | Interface management plan | 07_Interface_Management | Victoria Kulikova | ARC-009 | Draft | 3 | 2 | 1 | 0 | 16.67%
8 | Configuration management and data management baseline plan | 08_Configuration_Data_Management | Jash Joshi | MGT-007 | Draft | 3 | 0 | 3 | 0 | 50%
9 | Compliance check with maritime regulations | 09_Maritime_Compliance | Mikhail Timofeenko | REQ-005 | Draft | 1 | 0 | 1 | 0 | 50%
| Total |  |  |  |  | 37 | 10 | 27 | 0 | 36.49%
Progress counts a draft as half done and a baselined item as done.

## By member
Team member | Role | Responsible for | CIs owned | Planned | Draft | In review | Baselined
Vladislav Zagorodnyuk | MBSE and Requirements Engineer | Capella model (OA, SA) and diagrams; system and technical requirements; IDEF0 A4; simulations | 18 | 6 | 12 | 0 | 0
Victoria Kulikova | Functional & Interface Engineer and Architecture | IDEF0 A-0 and A0; logical architecture; N2; ICDs; interface management plan | 6 | 3 | 3 | 0 | 0
Jash Joshi | Stakeholders and Documentation Engineer, configuration manager (proposed) | Mission and NGO; stakeholders; ConOps; project management plan and WBS; CM/DM plan | 12 | 1 | 11 | 0 | 0
Mikhail Timofeenko | Safety, Risk, Reliability, Verification and Validation Engineer | Risk analysis; FMEA; reliability; V&V plans; maritime compliance check | 6 | 2 | 4 | 0 | 0
All (CM assembles) | Whole team | Review packages: PDR presentation | 1 | 1 | 0 | 0 | 0
Total |  |  | 43 | 13 | 30 | 0 | 0

## Folders
Folder | PDR item | CIs
01_MBSE_Model/capella | 1 | 1
01_MBSE_Model/diagrams/1_Operational_Analysis | 1 | 3
01_MBSE_Model/diagrams/2_System_Analysis | 1 | 5
01_MBSE_Model/diagrams/3_Logical_Architecture | 1 | 1
01_MBSE_Model/functional_analysis | 1 | 3
02_ConOps | 2 | 2
03_Requirements | 3 | 3
04_Project_Management | 4 | 4
05_Risk_Analysis | 5 | 3
06_Verification_Validation | 6 | 2
07_Interface_Management | 7 | 3
08_Configuration_Data_Management | 8 | 2
09_Maritime_Compliance | 9 | 1
analysis |  | 4
problem-sets/PS02_System_Analysis |  | 1
references |  | 2
reviews |  | 1
. |  | 2

## Baselines
Baseline | Review | Content | Git tag | Date | Status
Functional | SRR | Mission and NGO, stakeholders, system requirements, ConOps | srr-baseline |  | Planned
Allocated | PDR | All 9 PDR deliverables at v1.0 | pdr-v1.0 |  | Planned
Product | CDR | Detailed design (later phase) | cdr-v2.0 |  | Planned

## Change log
Date | CI ID | From version | To version | Change | Author | Issue / PR
2026-10-29 | MGT-001 | v0.1 | v0.2 | Register moved to the GitHub repository; file names without versions; official 9 PDR deliverables | Jash Joshi | initial commit
2026-10-29 | REQ-003 | v0.2 | v0.3 | Reduced to 11 SR and 32 TR with concrete values | Vladislav Zagorodnyuk | initial commit